## Sheet1
Client Name
Checklist Completed by:
Test Timeline | Market | Participation Required | Client Testing Requirement | Expected Outcome | Result | Comments
Saturday 19th October 2024 08h00 | All Markets | Mandatory | Download Friday’s End of Day files.
Saturday 19th October 2024 13h00-14h00 | All Markets | Mandatory | Failover to JSE DR and prove basic connectivity
|  | Mandatory | Login to the respective Markets/Gateways
|  | Mandatory | Connect to the JSE Market Communication page https://www.jse.co.za/services/technologies/market-communications | Successfully connect and view status updates on DR test
14h00 - 17h00 | Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files
|  | Mandatory | View start of day reference data | Successfully process and/or view SOD reference data
|  | Optional | Submit 1 order and 1 Off Book trade | successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  | Optional | Perform OOBD | Succesfully connect and recover open orders
|  | Optional | Perform OTBD | Successfully connect and recover trades for the current day.
|  | Optional | Login to BDA | Successfully login to BDA
|  | Optional | Login to FTP | Successfully login to FTP
|  | Optional | Download of BDA files | Successfully download BDA file
| Currency Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files
|  | Mandatory | View start of day reference data | Successfully process and/or view SOD reference data
|  | Optional | Submit 1 order and 1 Off Book trade | successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  | Optional | Perform OOBD | Succesfully connect and recover open orders
|  | Optional | Perform OTBD | Successfully connect and recover trades for the current day.
| Equity Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files
|  | Mandatory | View start of day reference data | Successfully process and/or view SOD reference data
|  | Optional | Submit 1 order and 1 Off Book trade | successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  | Optional | Perform OOBD | Succesfully connect and recover open orders
|  | Optional | Perform OTBD | Successfully connect and recover trades for the current day.
| Commodity Derivatives Market | Mandatory | Connectivity to CDM | Successfully connect to the NUTRON front-end or via the API
|  | Mandatory | View start of day reference data | Confirm reference data is viable on the front-end OR re-request start of day reference data via the API
|  | Optional | Submit 1 order and process 1 Off Book trade | successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  | Optional | Perform OOBD | Succesfully connect and recover open orders
|  | Optional | Perform OTBD | Successfully connect and recover trades for the current day.
| Interest Rate Derivatives Markets | Mandatory | Connectivity to IRD Market | Successfully connect to the NUTRON front-end or via the API
|  | Mandatory | View start of day reference data | Confirm reference data is viable on the front-end OR re-request start of day reference data via the API
|  | Optional | Submit 1 order and process 1 Off Book trade | Successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  | Optional | Perform OOBD | Succesfully connect and recover open orders
|  | Optional | Perform OTBD | Successfully connect and recover trades for the current day.
| International Access Point | Mandatory | Confirm the flow of EQM multicast data for all Market Data services
Confirm the flow of EDM multicast data for all Market Data services
Confirm the flow of FXM multicast data for all Market Data services
Confirm the flow of CDM multicast data for all Market Data services
| All Markets - Only those that have multicast service EDM, EQM and FXM | Live Information Subscribers (market Data) | Connectivity to Market Data Gateways | Successfully connect to Market Data Gateways
|  |  | Re-request start of day reference data | Successfully re-requested start of day reference data
|  |  | Confirm the flow of multicast data for all Market Data services | Confirm the flow of multicast data for all Market Data services
| All Markets | Non-Live Information Subscribers (market Data) | Connectivity to IDP | Successfully connect to IDP service
|  |  | Download of subscribed files | Download files as at Friday, 18 October 2024
| Derivatives Markets | Clearing Members | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API
|  |  | Connectivity to RTC | Log in and download and view reference data and positions
| All Markets | All participants | Ensure business readiness for Monday | Successfully remove test data
| All Markets | All participants | Confirmation of testing | Clients to notify CSC once their testing is complete
PLEASE EMAIL COMPLETED CHECKLIST TO CustomerSupport@jse.co.za and EnterpriseRiskManagement@jse.co.za
Test Timeline | Market | Participation Required | Client Testing Requirement | Expected Outcome | Result | Comments
Sunday 20th October 2024 10h00 - 11h00 | All Markets | All participants | Confirmation of participation | Clients to notify Customer Support once they are on site
10h00 - 11h00 | All Markets | All participants | Connect to the JSE Market Communication page https://www.jse.co.za/services/technologies/market-communications | Successfully connect and view status updates.
| Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Telnet to the Equity Market Trading and Market Data Gateways | Successfully receive and process reply
| Equity Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Telnet to the Equity Market Trading and Market Data Gateways | Successfully receive and process reply
| Currency Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Telnet to the Equity Market Trading and Market Data Gateways | Successfully receive and process reply
| Interest Rates Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API (Markets will be in a download state)
| Commodity Derivatives Markets | Members/Software Vendors/Shared Infrastructure Providers | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API (Markets will be in a download state)
| Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files for 18 October.
| Equity Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files for 18 October.
| Currency Derivatives Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files for 18 October.
| All Markets | All participants | Ensure business readiness for Monday | Successfully remove test data, if not already removed on Saturday
| All Markets | All participants | Confirmation of testing | Clients to notify CSS once their testing is complete
PLEASE EMAIL COMPLETED CHECKLIST TO CustomerSupport@jse.co.za and EnterpriseRiskManagement@jse.co.za