## Sheet1
Member Name
Name of Key Contact
Test Timeline | Market | Participation Required | Client Testing Requirement | Outcome | Result
| All Markets | All participants | Confirmation of testing | Clients to notify Client Service Centre (CSC) once they are on site
Saturday 03 October 2015 12h30 - 14h00 | All Markets | All JSE Clients | Failover to JSE DR and prove basic connectivity
Login to the respective Markets/Gateways
|  |  | Connect to the JSE Market Communication page: https://www.jse.co.za/services/technologies/market-communications | Successfully connect to the JSE website and view DR test status updates
14h00 - 17h00 | Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client reference data .CSV files | Connect to IDP service and retrieve client reference data files for 02 October 2015.
|  |  | Connect to the Equity Trading and Information Gateways | Successfully connect one CompID per software to each Gateway as per client set-up to JSE remote DR site.
|  |  | View start of day reference data | Successfully process and view SOD reference data
|  |  | Perform OOBD | Succesfully receive the latest status of their orders
|  |  | Submit 1 order and 1 Off Book trade | Successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  |  | Perform OTBD | Successfully connect and recover trades for the current day.
|  |  | Rerequest logins on MDGs | Clients to login to the MDGs and submit a rerequest.
|  |  | Confirm the Closing Price and Instrument ID of an instrument that was suspended on 03/10/2015 | Successfully process and confirm the details of the market data updates when an instrument is suspended.
|  |  | Confirm the Instrument Symbol and the time that a SENS announcement was sent out. | Successfully process and confirm the details of a SENS announcement.
| Equity Derivatives Market | Equity Derivatives Members | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API
|  |  | View start of day reference data | Confirm reference data is visible on the front-end OR re-request start of day reference data via the API
|  |  | Submit 1 order and 1 Off Book trade | Successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  |  | Perform deal management functions | E.g. Allocations, assigns,etc
| Commodity Derivatives Market | Commodity Derivatives Members | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API
|  |  | View start of day reference data | Confirm reference data is visible on the front-end OR re-request start of day reference data via the API
|  |  | Submit 1 order | Successfully submit 1 order receive acknowledgements
|  |  | Perform deal management functions; e.g. Allocations, assigns,etc | E.g. Allocations, assigns,etc
| Interest Rate and Currency Markets | Spot, Currency, and Bond Derivatives Members | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API
|  |  | View start of day reference data | Confirm reference data is visible on the front-end OR re-request start of day reference data via the API
|  |  | Submit 1 order and process 1 Off Book trade | Successfully submit 1 order and 1 Off Book trade and receive acknowledgements
|  |  | Perform deal management functions; e.g. Allocations, assigns,etc | E.g. Allocations, assigns,etc
| Equity Market | Information Subscribers | Rerequest logins on MDGs | Clients to login to the MDGs and submit a rerequest.
|  |  | Confirm the Closing Price and Intrsument ID of an instrument that was suspended on 03/10/2015 | Successfully process and confirm the details of the market data updates when an instrument is suspended.
|  |  | Confirm the Instrument Symbol and the time that a SENS announcement was sent out. | Successfully process and confirm the details of a SENS announcement.
| All Markets | Information Subscribers | Process Market Data | Process real time bids, offers and trades and download EOD files which are subscribed to (Equities, Indices, etc) for 02 October 2015
| Derivatives Markets | Clearing Members | Connectivity to NUTRON at JSE remote DR site | Successfully connect to the NUTRON front-end or via the API
|  |  | Download the balancing file from the previous EOD | Successfully download Deals file for 03 October 2015
| All Markets | All participants | Ensure business readiness for Monday, 05 October 2015.
| All Markets | All participants | Confirmation of testing | Clients to notify CSC once their testing is complete
PLEASE EMAIL COMPLETED CHECKLIST TO CustomerSupport@jse.co.za
Test Timeline | Market | Participation Required | Client Testing Requirement | Expected Outcome | Result
Sunday 04 October 2014 10h00 - 12h00 | All Markets | All participants | Confirmation of participation | Clients to notify CSC once they are on site
|  |  | Connect to the JSE Market Communication page https://www.jse.co.za/services/technologies/market-communications | Succesffully connect and view status updates.
| Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Telnet to the Equity Market Trading and Market Data Gateways | Successfully receive and process reply
| Derivatives Markets | All participants | Connectivity to NUTRON | Successfully connect to the NUTRON front-end or via the API (Markets will be in a download state)
| Equity Market | Members/Software Vendors/Shared Infrastructure Providers | Retrieve client .CSV files | Connect to IDP service and retrieve client reference data files for 02 October 2015
| All Markets | All participants | Ensure business readiness for Monday | Successfully remove test data, if not already removed on Saturday
| All Markets | All participants | Confirmation of testing | Clients to notify CSC once their testing is complete
PLEASE EMAIL COMPLETED CHECKLIST TO CustomerSupport@jse.co.za