## Slide 1: Nutron Repo Reporting Reform Key milestones
API specifications to be issued Mid July 2024
API software providers & developers dev Mid July to Mid October 2024
SYT with Strate Mid Sept – End Oct 2024
Internal Integration Testing Mid Nov – Early Jan 2025
SWP conformance testing Mid Nov – Early Jan 2025
Acceptance Testing by all Software contributors Mid Jan – Mid Feb 2025
Full Market (Client) Testing Mid Feb – Mid March 2025
Testing with Zaronia Mid March – Early May 2025
Mandatory Dress rehearsals End March & End April 2025
Go-live May 2025