A782

11 April 2007

Dear JSE Stakeholder

In keeping with the JSE’s commitment to inform all relevant stakeholders of progress on Project Orion on an

ongoing basis, we would like to communicate the Orion Release C status and inform the stakeholders of some

of the milestones reached to date and others that are coming up.

# Milestones:

# We have to date achieved and communicated the following:

| 1 February 2007 | Training Guidance Note issued for Derivatives Training |
| --- | --- |
| 9 February 2007 | Market Communication session conducted at the JSE Dates announced for Derivatives markets training |
| 12 February 2007 | Training bookings officially started |
| 14 February 2007 | User Connectivity Document issued to all stakeholders. All users were requested to complete and submit the attached NAS request by 09 March 2007 |
| 27 February 2007 | FAQ’s document posted on Project Orion website and updated on regular basis |
| 28 February 2007 | Release C API Specification document Version 1 Revision 15 issued to all stakeholders |
| 12 March 2007 | Technical Work Group session held at the JSE with software developers to discuss questions related to the new API Specifications document |
| 19 March 2007 | Training for Orion Release C Derivative members officially commenced at the JSE |
| 25 March 2007 | New Infomax Derivatives EOD Specifications published |
| 29 March 2007 | Stress tests conducted at the JSE on the new Derivatives trading solution |
| 02 April 2007 | External Release C test environment available First API developers successfully connected to the JSE external Release C test environment |

# The road ahead:

- Training

The JSE is currently conducting training at the JSE’s premises and is looking at providing sessions in Cape Town if required. We therefore request any users that require training in Cape Town to please contact Anthony Leibrandt (anthonyl@jse.co.za or +27 11 520 7475) for Equity Derivatives and Chris Sturgess (chriss@jse.co.za or +27 11 520 7299) for Agricultural Products training as soon as possible.

The number of delegates attending Derivatives markets training has reduced quite dramatically and                   therefore the JSE has consolidated the remaining sessions as follows:

- Financial Derivatives training will take place on 12 and 18 April 2007 only between 12h00 and 14h00

- Agricultural training will continue daily between 14h30 and 17h00 until 23 April 2007

# More days will be allocated once the current training slots are fully booked

- Conformance Testing

The JSE is aware of the fact that the Derivatives markets users and software solution providers have never previously participated in conformance testing; we will communicate in due course the nature of the conformance testing as well as the criteria that must be adhered too.

Conformance testing requires each user that wants to trade or receive public data on the derivatives markets to use software that has passed conformance testing. This is to ensure that the software operated by users will not negatively impact the JSE’s trading systems. Any user utilising the JSE’s front end software need not concern themselves with conformance, as the JSE will conform the JSE software on the users’ behalf. The JSE will provide as much assistance as possible to facilitate the conformance process by other software vendors/users.

Testing schedules and software conformance requirements will be made available to the market during the course of May 2007. This will also include time slots for these tests.

- External Release C Test environment

The external Release C test environment is now accessible to all members, software providers and Public Information Subscribers. To gain access to this environment it is vital that ALL stakeholders complete the Network Access System (NAS) form request that will enable the JSE to facilitate IP connectivity to this environment. Therefore all stakeholders are urgently required to submit the completed NAS document to NAS@jse,co,za

Once connectivity has been facilitated the JSE will provide members with the login details for the test environment. The JSE will provide members with the same set of access codes as are currently loaded in the Production systems. These login codes can be obtained from the Equity Derivatives and Agricultural Products Divisions.

The new Derivatives front end will be released to all members on 25 April 2007. In the meantime selected members that have successfully been converted to IP connectivity will be approached to test connectivity and the installation procedure for the new front end. A detailed installation document will be issued to ALL users closer to 25 April 2007.

Similarly Public Information subscribers can obtain login codes for the external Release C test environment from the Information Products Sales Division to test their new software. Subscribers can login to the environment, listen to heartbeat messages and download lists of available contracts. The JSE will endeavour to create activity in this environment to facilitate testing.

- Important Dates

Please take note of the dates below:

| 2 April 2007 | External test environment available Please contact Derivative_Info@jse.co.za to facilitate connectivity |
| --- | --- |
| 25 April 2007 | The new Trading Front-end will be made available The latest API document, containing minor changes, will be released |
| May 2007 | Market communication on external testing progress Issue Market Dress Rehearsal packs for Financial Derivatives Comprehensive End of Day data sets will be made available for download Conformance testing phase starts (to be confirmed) |
| June 2007 | Status update for Financial Derivatives ahead of Market Dress Rehearsals Issue Market Dress Rehearsal Packs for Agricultural Derivatives |
| 9 June 2007 | Market Dress Rehearsal 1 for Financial Derivatives |
| 23 June 2007 | Market Dress Rehearsal 2 for Financial Derivatives |
| 30 June 2007 | Market Dress Rehearsal 3 for Financial Derivatives (Live cut-over) |
| 2 July 2007 | Financial Derivatives Go-Live |
| July 2007 | Status update for Agricultural Derivatives ahead of Market Dress Rehearsals |
| 21 July 2007 | Market Dress Rehearsal 1 for Agricultural Derivatives |
| 4 August 2007 | Market Dress Rehearsal 2 for Agricultural Derivatives |
| 11 August 2007 | Market Dress Rehearsal 3 for Agricultural Derivatives (Live cut-over) |
| 13 August 2007 | Agricultural Derivatives Go-Live |

# Should you have any questions or queries, please do not hesitate to contact us via either your Business

Owner, or directly on our email address Derivative_Info@jse.co.za

Business contacts:

Chris Sturgess		– Agricultural Derivatives		–  ChrisS@jse.co.za	- 011 520 7299

Anthony Leibrandt	– Financial Derivatives		–  AnthonyL@jse.co.za	- 011 520 7475

Miranda Maja		– Financial Derivatives		– MirandaM@jse.co.za	- 011 520 7098

Neil Vendeiro		– Information Subscribers         	– NeilV@jse.co.za	- 011 520 7333

Matthias Kempgen	– Software Developers		– MatthiasK@jse.co.za	- 011 520 7069

Yours sincerely,

# Julius Frauendorf

User Readiness