NoteA964B

JSE Derivatives System Replacement Market Dress Rehearsal Pack

| Created by: | DSR team |
| --- | --- |
| Date: | Sept 2008 |
| Version | 25 Sept v1 |

This document is confidential and contains property belonging to the JSE Limited (the JSE).  Neither this document nor its contents may be disclosed to a third party, nor may it be copied, without the JSE's prior written consent.

The JSE endeavours to ensure that the data and other material in this document are correct and complete but does not accept any liability for error herein or omission here from.  The development of JSE products and services is continuous and published information may not be up to date.  It is important that you check the current position with the JSE before acting on any information in this document.

TABLE OF CONTENTS

1. 	Introduction	3

1.1.	Document Purpose	3

1.2.	Readership	3

2. 	Objectives of the Market Dress Rehearsal	3

3. 	Market Dress Rehearsal Schedule and Tracking	3

3.1.	Market Dress Rehearsal Schedule	3

3.2.	Dress Rehearsal Tracking	3

3.3.	Pre Requisites	3

3.3.	Success / Pass Criteria	3

4. 	Participant Responsibilities and Data Guidelines	3

4.1.	Participant Responsibilities	3

4.2.	Data Guidelines	3

4.2.	Communication	3

5. 	Additional Information and Queries	3

6.	Market Dress Rehearsal Functional Testing Checklist	3

7. 	Market Dress Rehearsal Detailed Checklist	3

# 1. 	Introduction

## 1.1.	Document Purpose

This document is intended to outline the objectives, schedule and data guidelines for the JSE Derivative System Replacement Dress Rehearsals for the Agricultural Derivative Market.  It also includes a detailed checklist that must be completed by all participants in the Dress Rehearsal and returned to the JSE.

| Dress Rehearsal 1 | 19 July 2008 | Mandatory Business testing | 08H30 – 15H00 |
| --- | --- | --- | --- |
| Dress Rehearsal 2 for ED Dress Rehearsal 1 for AD | 02 August 2008 | Mandatory Business testing | 08H30 – 15H00 |
| Pre go-live ED | 16 August 2008 | Mandatory Business testing | 08H30 – 15H00 |
| Dress Rehearsal 2 for AD | 4 October 2008 | Mandatory Business testing | 08H30 – 13H30 |
| Pre go-live AD | 18 October 2008 | Mandatory Business testing | 08H30 – 15H00 |

## 1.2.	Readership

The intended audience for this document includes:

- JSE Agricultural Derivative market participants (trading and clearing members)

- JSE Agricultural Derivative members with logins on the Equity Derivative Market

- JSE API Software Providers

- Information subscribers

Please note that the Equity Derivatives Market will be open for the purpose of this test – we require all Agricultural customers that also trade in the EDM Market to log into both markets for the purpose of this test.

Trading members and information providers are requested to analyse the impact to their available bandwidth when interacting with both markets during this test.

# 2. 	Objectives of the Market Dress Rehearsal

The objectives of the JSE Dress Rehearsal are to:

- Practise the cut over activities required for Go Live

- Simulate selected trading on the new Derivatives Markets

- Gauge overall level of readiness across all Stakeholders

- Identify any critical issues that need to be addressed prior to Go live

- Build internal and external confidence for Go Live

- Minimise the risk of unexpected issues on Go Live day

- Provide Users with an opportunity to test their front-end solutions and related systems on the production environment

- Provide API developers with opportunity to prove systems in near production  environment

- Prove existing internal JSE application readiness for Go Live

- Prove EOD processes and other after market activities

Note:  Apart from a scheduled period of volume testing (See Section 6 - Functional Testing Schedule) the overall objective of the JSE Derivative Market Dress Rehearsals is NOT that of a stress test.

# 3. 	Market Dress Rehearsal Schedule and Tracking

## 3.1.	Market Dress Rehearsal Schedule

The JSE Derivatives Market Dress Rehearsals will take place on 3 separate weekends per market.  This is in addition to all user firms own testing and connectivity preparations to the new system prior to the Dress Rehearsals and Go-Live.

Saturday schedules

| A | JSE System start up | 07h30 – 08h00 |
| --- | --- | --- |
| B | System Online (Users Log in) | 08h30 – 09h00 |
| C | Trading APD Market EDM Market | 09h10 – 11h45 09h00 - 12h00 |
| D | End of Day activities | 12h00 – 13h30 |

Please Note:

- The JSE will available for support throughout the test

- Technical activities include any technical tests as well as confirming the restore against SAFEX to provide business readiness for Monday 6 October

## 3.2.	Dress Rehearsal Tracking

The JSE Derivative Market Dress Rehearsal Detailed Checklist (Section 7 of this document) will be used as a measure of success of a participant in the JSE Derivative Market Dress Rehearsal.  A single checklist per participant Firm must be completed by a nominated representative and must be signed off by both the Head of Trading and an IT representative.

The completed Detailed Checklist must be submitted electronically and be faxed to the JSE by the latest 10h00, the Monday post the Dress Rehearsal Weekend.   The contact details are provided below:

E-mail:		Derivative_Info@jse.co.za

Fax:		011 - 520 7551 / 7198 / 8592

## 3.3.	Pre Requisites

The following have been outlined as pre requisites for the JSE Derivative Market Dress Rehearsal:

- Trading and Clearing Users must have attended training or be comfortable with the new application

- Network connection to the new application has been requested and tested

- Application must be configured (specifically for production environment) and ready to trade or receive data

- Have logged in at least once to production environment

- Have received and configured all production user codes from JSE

- API software providers and Information Subscribers must have passed conformance

- Key responsible person identified and communicated to the JSE prior to test

If Pre requisites are not met, the user may not participate in the Dress Rehearsal.

## 3.3.	Success / Pass Criteria

The following have been outlined as success / pass criteria for the JSE Derivative Market Dress Rehearsal:

- User ability to connect and trade

- 100% interactive participation throughout the test period - Number of traders logged on

- Adherence to the test schedule and conditions

- Adherence to realistic order details and prices

- Adherence to normal trading and volume activity - Order and trade data generated per trader except for volume test

- Completed and signed test checklists / results returned to the JSE

- Completed and signed declaration that functionality and data integrity was intact

- All problems are logged

- No excessive re-requests of data during the tests

- Limited system errors generated by users in system logs

# 4. 	Participant Responsibilities and Data Guidelines

## 4.1.	Participant Responsibilities

The following list details the responsibilities of all JSE Derivative Market Dress Rehearsal participants:

- Participants are responsible for all of their own environment preparations, connectivity and reference data download

- All users to log on and participate in the test

- Ensure that all fields are displayed correctly and as expected

- Ensure that all fields are enterable as expected

- Check that invalid field entries are not allowed

- Check that you have access to all functionality that you expect and not more or less

- Does all this functionality operate as expected

- Regular checkpoints will be communicated throughout the test by the JSE.  Any participant falling behind the schedule must communicate this to the JSE as soon as possible.  Likewise if the schedule is required to change, this will also be communicated to the market.

- All Software bugs may be logged and sent to the JSE. Any other issue encountered during Dress Rehearsal must be logged with JSE Client Services (011-520 7777)

## 4.2.	Data Guidelines

The following are key data guidelines:

- Valid user codes and passwords must be used for all application access

- Realistic prices and volumes must be entered

- Data will be converted from production for the Dress Rehearsals and should therefore be correct data

## 4.2.	Communication

The JSE will communicate with all testers in a number of different ways:

- A message via the front end

- An email to all known email addresses

- An SMS to known cell phone numbers

The JSE will communicate progress, issues and status of the tests using the above communication mechanisms. Please ensure that JSE Customer Services has your correct contact information.

# 5. 	Additional Information and Queries

Any JSE Derivative Market Dress Rehearsal queries can be directed to JSE Client Services on 011 520 7777 or Derivative_Info@jse.co.za

| APD External Dress Rehearsal 04 October 2008 |
| --- |
| DRESS REHEARSAL SCHEDULE |
| Ref # | Trading Phase | Trading Times | Functionality to be tested |
|  |  | (SAST) | (High-level Description) |
| Checkpoint 1 - Roll Back Completed Successfully |
| MONDAY - THURSDAY 29 September 2008 - 02 October 2008 |
| A | Balancing of Environments | 13h00 – 17h00 | JSE to balance APD Production and APD Replacement Environments |
| Checkpoint 2 - Balancing of Environments Completed |
| FRIDAY - 03 October 2008 |
| A | Balancing of Environments | 13h00 – 17h00 | JSE to balance Production and Derivatives Replacement Environments |
| Checkpoint 3 - Balancing of Environments Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| B | Set Saturday as a Trading day and set Market Times | 17h00 – 18h00 |  |
| C | ALL users to check logins to prod environment | All day | All internal users to check their logins to the production environment |
| D | Backup of Environments | 00H00 – 03H00 | JSE and Clearing Member Technical teams to make a Backup of theAPD and EDM Derivatives Replacement environment, for Rollback purposes |
| Checkpoint 4 – Setup of Environments Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: Friday Balancing completed” |
| SATURDAY - 04 October 2008 |
| α | Arrival on Site | 07h30 |  |
| A | JSE Market Startup | 07h30 – 08h00 | Check File Preparation complete |
|  |  |  | Check Market times |
| Checkpoint 1 – Market Startup Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: Market startup is complete and market is in a download state” |
| B | All users log in | 08h30 – 09h00 | All front ends login |
| Checkpoint 2 - User Login Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: All market logins should be complete - Open Order period commencing” |
| C | Auction EDM / start of continuous trading | 9h00 - 09h05 09h05 | EDM Market in Opening Auction on ALSI ONLY Continuous Trading on ALL EDM contracts from 09h05 |
| D | Open Order Period (only APD) | 09h10 - 09h19 | APD - Users may enter orders, orders will appear in their Active Orders file, but not on screen |
|  |  |  | All - testing and system monitoring - this includes Networks, AM and IM. |
| Checkpoint 3 – Open Order & Auction Period Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: APD - Open Order period complete, Market in continuous trading” |
| D | Continuous Trading APD | 09h20 - 11h30 | Order entry and Order deletion |
|  |  |  | Client reference modification |
|  |  |  | Client Loading |
|  |  |  | Trade reporting – Assigned trades, Dividing trades |
|  |  |  | Manual trade Correction (new functionality) |
|  |  |  | Option exercise |
|  |  |  | View Position updates |
|  |  |  | Physical deliveries (APD) |
|  |  |  | Order matching |
|  |  |  | Deal Management |
|  |  |  | Capture Daily Rates |
|  |  |  | Checking of Delayed Feed on JSE website. |
|  |  |  | Viewing of Static files and file downloads |
| E | Continuous Trading EDM | 09h05 - 11h45 |  |
| Checkpoint 4 - Continuous Trading Phase Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: APD continous trading phase complete - ADMIN period commencing now. |
| F | Admin Period APD | 11h30 - 11h45 | No On Screen Trading |
|  |  |  | Physical Deliveries (APD) |
|  |  |  | Allocations allowed |
|  |  |  | / Post Trade activities |
|  |  |  | Deal Management allowed |
| G | Admin Period EDM | 11h45 - 12h00 | No On Screen Trading |
|  |  |  | Report only trades allowed |
|  |  |  | Allocations allowed |
|  |  |  | / Post Trade activities |
|  |  |  | Deal Management allowed |
| Checkpoint 6 - Admin Period Completed |  |  |  |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: Admin period complete for APD” |
| H | Market moves into Download ONLY | 11h45 | Download ONLY |
|  |  |  | Users may download EOD data (e.g. deals, positions) via API or JSE Front End |
| Checkpoint 7 - Market Closed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: APD Market in download only - MTM download available shortly ” |
| I | Exchange runs EOD for APD | 11h45 - 12h45 |  |
| J | Create files/reports for Clearing Members | 12h45 - 13h15 | Mark to Market File made available for Clearing members to run their processes (File is available for download by all users, but may change when the Clearing members balance to the JSE) |
|  |  |  | Daily account summary made available for Clearing Members |
| Checkpoint 8 - End of Day Run and Clearing Member Files Completed |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: APD EOD Run complete” |
| K | EOD Processes & Downloads | 13h15 - 13h30 | JSE produces files for BDA & CAPAD |
|  |  |  | JSE produces Billing files for ACCPAC |
|  |  |  | Generation of Swift Payment Instruction Messages |
|  |  |  | Users download MTM file via API, after Clearing members would have balanced above. |
|  |  |  | EOD reports sent to website (‘Free to Air’) |
|  |  |  | EOD structured files available to subscribers on FTP server |
| L | Submit completed checklist to the JSE |  | Please ensure checklist is complete and signed and return to the JSE. |
|  |  |  | Clearing Members & Information Subscribers may go home. |
| Checkpoint 9 - End of Functional Testing (13H45) |
| The web page will be updated with status and any comments |
| A message will be posted on the front end |
| Email notification will be sent |
| SMS: “Derivatives Replacement DR Status: APD External Dress Rehearsal complete - Thank you!” |
| M | Roll back | 13h30 | JSE to restore Friday night backups to New environment. EDM business to perform checks on ALL reference and trade data APD to ensure system is ready to continue parallel run on Monday 06 October 2008 |
| Checkpoint 10 - Roll Back Completed Successful |

# Market Dress Rehearsal Functional Testing Checklist

| Friday: Clearing Member participation mandatory |
| --- |
| CM – Clearing Members |
| APD – APD Members |
| EDM – EDM Members |
| IS – Information Subscribers |
| Trading Phase |  | Ref # | Action / Event | Expected Result | Applicable To | Completed (Y/N) | Successful (Y/N) | Comments |
| Check Point 1 |
| Clearing Member Balancing | 13h00 | A1 | Clearing Members to balance both SAFEX Production and derivative Replacement production environment | Clearing Members balance and have correct MTM, Deals and Positions files for Friday | CM |  |  |  |
| Check point 2 |
| Friday: Backup of Environments | After Balancing | B1 | JSE backs up Derivative replacement production environment, for Rollback purposes after Dress Rehearsals | JSE Derivative replacement | JSE |  |  |  |
|  |  |  |  | Production environment |  |  |  |  |
|  |  |  |  | backed up |  |  |  |  |
|  |  | B2 | Clearing Members backup their systems, for Rollback purposes after Dress Rehearsals | Clearing Members’ | CM |  |  |  |
|  |  |  |  | Derivative replacement environments |  |  |  |  |
|  |  |  |  | backed up |  |  |  |  |
| Saturday: Full participation mandatory |
| Note: The shaded steps are performed by the JSE and have been included for a level of functional understanding. Reference numbers highlighted in yellow indicates technical actions and in blue indicates business steps. |
| CM – Clearing Members |
| APD – APD Members |
| EDM – EDM Members |
| IS – Information Subscribers |
| Phase |  | Ref # | Action / Event | Expected Result | Applicable To | Completed (Y/N) | Successful (Y/N) | Comments |
| Saturday: Market Startup | 07h30 | A1 | File preparation | Market started | JSE |  |  |  |
|  |  |  | Check market times |  |  |  |  |  |
|  |  |  | Check Autoquote engine startup |  |  |  |  |  |
|  |  |  | Check Single Stock Future mappings |  |  |  |  |  |
| Check Point 1 |
| Saturday: User Login | 08h30 – 09h00 | B1 | All API users, JSE Font End users and Information Users login | Users logged into market | CM APD EDM IS |  |  |  |
| Saturday: Market Download & Subscription Period |  | B2 | All users subscribe to required messages. Users subscribe to required contracts JSE Front End users setup their Trading Screens. API users send messages to request contracts. API users download required files (users of JSE FE receive these automatically on log in) | Users have subscribed to required messages JSE Front End Users’ trading screens are setup. API Users have subscribed to required contracts API users have downloaded required files. | CM APD EDM IS |  |  |  |
| Check Point 2 |
| Saturday: Open Order Period | 09h10 – 09h19 | C1 | APD Market Users enter orders during the open order period | Orders appear in users’ Active Orders view, but not on screen | CM APD EDM IS |  |  |  |
|  |  | C2 | EDM MARKET Users enter orders during the Auction period (starts when 5min to Market Open announcement is displayed, 09h00 – 09h05) | Best bid and ask of orders entered during the Auction Period are matched and Opening Price calculated | CM EDM IS |  |  |  |
| Check Point 3 |
| Saturday: Continuous Trading | APD - 09h20 – 11h30 EDM – 09h05 – 11h45 | D1 | Insert Orders (SSF’s, Index Futures , Agricultural Futures, Options, Can-Do Options, Splits, Spreads etc) | Orders inserted | CM APD EDM IS |  |  |  |
|  |  | D2 | Delete & Suspend orders | Orders suspended/deleted | CM APD EDM |  |  |  |
|  |  | D3 | Resubmit Orders | Orders resubmitted | CM APD EDM |  |  |  |
|  |  | D4 | Reduce Orders | Orders reduced | CM ADP EDM |  |  |  |
|  |  | D5 | Edit Orders | Orders edited | CM APD EDM |  |  |  |
|  |  | D6 | Cancel Orders | Orders cancelled | CM APD EDM |  |  |  |
|  |  | D7 | Information Subscribers listen to Screen / Price Updates. | Screen / Price Updates received. | IS CM APD EDM |  |  |  |
|  |  | D7 | Enter Report Only Trades | Report Only orders entered, NOT APPLICABLE TO APD | CM EDM |  |  |  |
|  |  | D8 | Accept Report Only trades | Report Only/ Assigned orders accepted | CM APD EDM |  |  |  |
|  |  | D9 | Option Exercise | Options exercised | CM APD EDM |  |  |  |
|  |  | D10 | Enter Tri-partite Deal | Tri-partite Deal entered | CM APD EDM |  |  |  |
|  |  | D11 | Roll position forward | Position closed out and booked into another position | CM APD EDM |  |  |  |
|  |  | D12 | Load Clients | Clients loaded | CM APD EDM |  |  |  |
|  |  | D13 | Edit Clients | Clients details updated | CM APD EDM |  |  |  |
|  |  | D14 | Assign trades | Trades assigned | CM APD EDM |  |  |  |
|  |  | D15 | Div Trades | Trades are Divided | CM APD EDM |  |  |  |
|  |  | D16 | Cumulate Trades | Trades cumulated | CM APD EDM |  |  |  |
|  |  | D17 | Silo Receipts & Physical Deliveries | Silo Certificates and Delivery Notices entered | CM APD |  |  |  |
|  |  | D18 | Check Delayed Data Feed on web | Delayed feed available on web | CM APD EDM IS |  |  |  |
| Check Point 4 |
| Saturday: Admin Period | APD - 11h30 – 11h45 EDM – 11h45 – 12h00 | F1 | Entry of Report only trades (No On Screen Trading Allowed) | Report Only trades entered – Not applicable to APD members | CM EDM |  |  |  |
|  |  | F2 | Report Only trades edited | Report Only trades edited – Not applicable to APD members | CM EDM |  |  |  |
|  |  | F3 | Accepting/rejecting report only trades | Report Only trades accepted/rejected – Not applicable to APD members | CM EDM |  |  |  |
|  |  | F4 | Assign (allocate) trades | Trades assigned | CM APD EDM |  |  |  |
|  |  | F5 | Split Trades | Trades split | CM APD EDM |  |  |  |
|  |  | F6 | Cumulate Trades | Trades cumulated | CM APD EDM |  |  |  |
|  |  | F7 | Silo Receipts & Physical Deliveries | Silo Certificates and Delivery Notices entered | CM APD |  |  |  |
|  |  | F8 | Adding a New Client | New Client is added | CM APD EDM |  |  |  |
| Check Point 5 |
| Saturday: Market Closed | APD - 11h45 EDM – 12h00 | G1 | Market Closes | Market Closed – Market in download only |  |  |  |  |
| Check Point 6 |
| Saturday: Run EOD | APD - 12h00 – 12h45 | H1 | Exchange performs EOD run (MTM & Margining) | EOD run successfully | JSE |  |  |  |
| Check Point 7 |
| Saturday: Clearing Member Balancing | APD - 12h45-13h15 | I1 | Make MTM File available for download | MTM File available for download (by all participants) | JSE |  |  |  |
|  |  | I2 | Make Daily Account Summary available for download | Daily Account Summary available for download | JSE |  |  |  |
|  |  | I3 | Clearing Members advised by Exchange that MTM file and Daily Account Summary can be downloaded | Clearing members notified | JSE |  |  |  |
|  |  | I4 | Clearing Members download MTM file & Daily Account Summary | MTM and Daily Account Summary downloaded | CM IS |  |  |  |
|  |  | I5 | Clearing Members run their EOD processes | Clearing Members processes run including physical deliveries | CM |  |  |  |
|  |  | I6 | Clearing Members balance to Exchange | Clearing Members balanced to Exchange | CM IS |  |  |  |
| Check Point 8 |
| Saturday: EOD Downloads | APD - 13h15 - 13h30 | J1 | Billing files for ACCPAC generated | Billing files for ACCPAC generated | JSE |  |  |  |
|  |  | J2 | SWIFT payment instruction messages generated | SWIFT payment instruction messages generated | JSE |  |  |  |
|  |  | J3 | Files for BDA & CAPAD generated | Files for BDA & CAPAD generated | JSE |  |  |  |
|  |  | J4 | Create EOD Reports | EOD Reports created | JSE |  |  |  |
|  |  | J5 | Create EOD Files | EOD Files created | JSE |  |  |  |
|  |  | J6 | API Users, Front End users and Information users download MTM file | MTM file downloaded, physical deliveries (APD) also available for download | CM APD EDM IS |  |  |  |
|  |  | J7 | Subscribers download EOD files | EOD files downloaded | IS |  |  |  |
|  |  | J8 | EOD Reports to SAFEX web site (free to air) | EOD reports can be viewed on web | CM APD EDM IS |  |  |  |
| Trading Phase |  | Ref # | Action / Event | Expected Result | Applicable To | Completed (Y/N) | Successful (Y/N) | Comments |
| Saturday: Rollback to environments - Full TECHNICAL participation mandatory |
| Note: This is to restore Derivative replacement systems to their state as at end of Friday, so that production parallel can continue on Monday. |
| Saturday Roll Back | APD and EDIM 13h30 | L1 | JSE to Roll back their Environment to state as at Friday | Successful Rollback of systems | JSE |  |  |  |
|  |  | L2 | Clearing Members to Roll Back their systems to state as at Friday | Successful Rollback of systems | CM |  |  |  |

# 7. 	Market Dress Rehearsal Detailed Checklist

To be returned to the JSE as per instructions in Section 3.2.

Member Firm Name:_______________________________	Date:_____________________

Market Dress Rehearsal Detailed Check-list completed by:

Name:				_______________________________

Position:			_______________________________

Company code /Member ID:	_______________________________

Signature			_______________________________

I hereby declare that all information contained here-in is an accurate reflection of the test conditions executed on behalf of my organisation.

Signed by Head of Trading:

Name:		_______________________________

Signature	_______________________________

Signed by IT representative:

Name:		_______________________________

Signature	_______________________________

General Comments: _____________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________