JSE AGRICULTURAL PRODUCTS MARKET NOTICE

Number	A964A

Date		25 September 2008

Dear Stakeholder,

DERIVATIVE SYSTEM REPLACEMENT – STATUS UPDATE -  AGRICULTURAL MARKET MANDATORY DRESS REHEARSAL

The JSE is pleased to confirm we have completed deployment of the new system for the Equity Derivative market and now plan to proceed to our deployment milestones for the Agricultural Derivative market system.

Our next milestone is the mandatory dress rehearsal for AD market participants (milestone 13). Participants for this dress rehearsal include trading members, clearing members, API providers and information subscribers. The JSE would like to re-iterate that this is a mandatory Dress Rehearsal for any participants that wish to go live on the new Agricultural Derivatives Market System (Nutron).

In an effort to allow all stakeholders to prepare for the deployment of the new systems, the JSE would like to re-iterate the envisaged deployment plans as previously communicated to the market.

While the JSE is currently on track with this plan, it should be noted that a final status checkpoint has been built into the plan to review the status after the mandatory market Dress Rehearsal, and if critical issues arise, alternative dates may be announced which will impact all subsequent dates. The JSE commits to continuing its market communications as per the remaining checkpoints in order to update stakeholders with the latest status and, if relevant, updated schedules and dates.

The high level market facing milestones remain as follows:

| Milestone | Milestone Description | Date | Status |
| --- | --- | --- | --- |
| 1 | JSE Deployment checkpoint 1 | Week of 26 - 30 May | COMPLETE |
| 2 | Final internal JSE testing completes | End June | COMPLETE |
| 3 | JSE Deployment checkpoint 2 | Week of 23 – 27 June | COMPLETE |
| 4 | JSE internal Dress Rehearsal | 12 July | COMPLETE |
| 5 | JSE Deployment checkpoint 3 | 15 July | COMPLETE |
| 6 | Equity Derivative Market (EDM) Dress Rehearsal 1 | 19 July | COMPLETE |
| 7 | EDM Dress Rehearsal 2 combined with Agricultural Derivative Market (ADM) Dress Rehearsal 1 | 2 August | COMPLETE |
| 8 | JSE Deployment checkpoint 4 | 5 August | COMPLETE |
| 9 | EDM pre Go-Live Dress Rehearsal | 16 August | COMPLETE |
| 10 | EDM Go-Live | 18 August | COMPLETE |
| 11 | EDM Go-Live Contingency | 25 August | NOT REQ |
| 12 | JSE Deployment checkpoint 5 | 9 September | COMPLETE |
| 13 | ADM Dress Rehearsal 2 | 4 October |  |
| 14 | JSE Deployment checkpoint 6 | 8 October |  |
| 15 | ADM pre Go-Live Dress Rehearsal | 18 October |  |
| 16 | ADM Go-Live | 20 October |  |
| 17 | ADM Go-Live Contingency | 27 October |  |

It is imperative that stakeholders ensure they are prepared for the AD system implementation.  Stakeholders are again reminded that the External test environment is available for any testing.

The JSE has commenced running parallel with Clearing members in an effort to ensure readiness for the Dress Rehearsal on Saturday 4 October. No testing can therefore take place on the pre-production environment. All ADM participants are requested to obtain Users codes from their JSE contacts and to connect and log on to the pre-production environment (10.3.5.131 Port 2210) to ensure readiness for the dress rehearsal prior to Saturday 4th October. Please find the connectivity document and the updated Market Dress rehearsal schedule and checklist, attached to this communication. The ADM will continue to run both the old and new replacement system in parallel until its scheduled go live date.

The JSE requires the following Key contacts per customer to ensure good communication is maintained throughout the Dress Rehearsals:

- Primary Business Contact

- Primary IT Contact

Information required for the above is:

Name

Surname

Telephone

Fax

Cell phone

Email address

Please forward the above details to Catherine de Klerk at E-Mail catherinedk@jse.co.za

or contact number +27(0)11 520 7659 as soon as possible.

The JSE appreciates your continued support for this initiative. Please address any queries to the relevant business owners or derivative_info@jse.co.za.