NoteA1130B

JSE Yield-X Market Dress Rehearsal  Schedule & Checklist

| Created by: | Matthias Kempgen |
| --- | --- |
| Approved by: |  |
| Date: | 27 October 2009 |
| Version | 3.0 |

This document is confidential and contains property belonging to the JSE Limited (the JSE).  Neither this document nor its contents may be disclosed to a third party, nor may it be copied, without the JSE's prior written consent.

The JSE endeavours to ensure that the data and other material in this document are correct and complete but does not accept any liability for error herein or omission here from.  The development of JSE products and services is continuous and published information may not be up to date.  It is important that you check the current position with the JSE before acting on any information in this document.

TABLE OF CONTENTS

1. 	Introduction	3

1.1.	Document Purpose	3

1.2.	Readership	3

2. 	Objectives of the Market Dress Rehearsal	3

3. 	Market Dress Rehearsal Schedule and Tracking	4

3.1.	Market Dress Rehearsal Schedule	4

3.2.	Dress Rehearsal Tracking	5

3.3.	Pre Requisites	6

3.3.	Success / Pass Criteria	6

4. 	Participant Responsibilities and Data Guidelines	6

4.1.	Participant Responsibilities	6

4.2.	Data Guidelines	7

4.2.	Communication	7

6.	 Market Dress Rehearsal Functional Testing Checklist	10

7. 	Market Dress Rehearsal Detailed Checklist	17

# 1. 	Introduction

## 1.1.	Document Purpose

This document is intended to outline the objectives, schedule and data guidelines for the JSE Yield-X Dress Rehearsal.  It also includes a detailed checklist that must be completed by all participants in the Dress Rehearsal and returned to the JSE.

| Description | Date | Focus | Times (SAST) | Required Testing | Environment |
| --- | --- | --- | --- | --- | --- |
| Dress Rehearsal 1 | 31 October 2009 | Mandatory Business and Technical Testing | 08h00 – 14h00 | Yield-X Nutron EDM Nutron * CDD Nutron * | Production |
| Dress Rehearsal 2 | 07 November 2009 | Mandatory Business and Technical Testing | 08h00 – 11h45 | Yield-X Nutron | Production |
| Connectivity Test pre-go live | 14 November 2009 | Mandatory Connectivity Testing in preparation for go-live | 09h00 – 11h00 | Yield-X Nutron | Production |
| Go-Live | 16 November 2009 |  |  | Yield-X Nutron | Production |

* All firms that have access to EDM and/or CDD NUTRON front ends are required to log in for these tests

## 1.2.	Readership

The intended audience for this document includes:

- JSE Yield-X market participants (trading and clearing members)

- Yield-X API Software Providers

- Yield-X Information subscribers

# 2. 	Objectives of the Market Dress Rehearsal

The objectives of the JSE Yield-X Dress Rehearsals are to:

- Practise the cut over activities required for Go Live

- Simulate selected trading on the new Yield-X Market

- Simulate Commodity Derivatives and Equity Derivatives Market trading activity simultaneously to conducting the Yield-X dress rehearsals for members who also trade on these markets

- Gauge overall level of readiness across all Stakeholders

- Identify any critical issues that need to be addressed prior to Go live

- Build internal and external confidence for Go Live

- Minimise the risk of unexpected issues on Go Live day

- Provide Users with an opportunity to test their front-end solutions and related systems on the production environment

- Provide API developers with opportunity to prove systems in near production  environment

- Prove existing internal JSE application readiness for Go Live

- Prove EOD processes and other after market activities

Note:  Apart from a brief, scheduled period of volume testing (See Section 6 – Functional Testing Schedule) the overall objective of the JSE Yield-X Market Dress Rehearsal is NOT that of a stress test.

# 3. 	Market Dress Rehearsal Schedule and Tracking

## 3.1.	Market Dress Rehearsal Schedule

The JSE Yield-X Market Dress Rehearsals will take place on 3 separate weekends.  This is in addition to all user firms own testing and connectivity preparations to the new system prior to the Dress Rehearsals and Go-Live.

Saturday 31 October 2009

| Technical | Yield-X start up | 08H00 – 09H00 |
| --- | --- | --- |
| Business | Business Functional Testing (Trading) | 09H00 – 11h45 |
| Business | Business Functional Testing (Clearing) | 11h45 – 13h00 |

Saturday 07 November 2009

| Technical | Yield-X start up | 08H00 – 09H00 |
| --- | --- | --- |
| Business | Business Functional Testing | 09H00 – 11H45 |

Saturday 14 November 2009

Whilst activities on this test day are predominantly technical it is recommended that at least one business user be available to sign-off readiness for Go Live.

| Technical | Connectivity Test ahead of go-live | 09H00 – 11H00 |
| --- | --- | --- |
| Technical | Margin re-conversion for deployment preparation | 11H00 – 13H00 |

Please Note:

- A period of volume testing has been scheduled for 30min from 11H00 – 11H30 on both 31 October 2009 and 7 November 2009. All users are requested to increase order activity during these times.

- Any tests which are not successful on the 31st October will need to be re-tested on 7 November.

- The Dress Rehearsal on 31 October 2009 will include balancing to clearing members for the deals done during that day’s trading session. The JSE will publish closing prices as they would in a live scenario post the trading session. The JSE and all Clearing Members are thus required to roll back their systems post this day’s activities to resume with the parallel run on Monday 02 November 2009. The Dress Rehearsal on 07 November 2009 will NOT include balancing to clearing members post the trading session unless the 31 October balancing was problematic.

- The JSE will available for support throughout the test

- Connectivity Details for the purpose of the Dress Rehearsals are as follows:

- Yield-X

IP  196.216.152.131  Port 2269 (Trading Engine)  Port 4469 (Front end download)

- EDM

IP  196.216.152.131  Port 2003 (Trading Engine)

- APD

IP  196.216.152.131  Port 2210 (Trading Engine)

## 3.2.	Dress Rehearsal Tracking

The JSE Yield-X Market Dress Rehearsal Detailed Checklist (Section 7 of this document) will be used as a measure of success of a participant in the JSE Yield-X Market Dress Rehearsal.  A single checklist per participant Firm must be completed by a nominated representative and must be signed off by both the Head of Trading (for Trading members) and an IT representative.

The completed Detailed Checklist must be submitted electronically and be faxed to the JSE by the latest 10h00, the Monday post the Dress Rehearsal Weekend.   The contact details are provided below:

E-mail:		yield-x_info@jse.co.za

Fax:		011 - 520 8659

## 3.3.	Pre Requisites

The following have been outlined as pre requisites for the JSE Yield-X Market Dress Rehearsal:

- Trading and Clearing Users must have familiarised themselves with the new application

- Network connection to the new application has been requested and tested

- Application must be configured (specifically for production environment) and ready to trade or receive data

- Have logged in at least once to production environment

- Have received and configured all production user codes from JSE

- API software providers and Information Subscribers must have started conformance

- Key responsible person identified and communicated to the JSE prior to test

If Pre requisites are not met, the user may not participate in the Dress Rehearsal.

## 3.3.	Success / Pass Criteria

The following have been outlined as success / pass criteria for the JSE Yield-X Market Dress Rehearsal:

- User ability to connect and trade

- 100% interactive participation throughout the test period - Number of traders logged on

- Adherence to the test schedule and conditions

- Adherence to realistic order details and prices

- Adherence to normal trading and volume activity - Order and trade data generated per trader except for volume test

- Completed and signed test checklists / results returned to the JSE

- Completed and signed declaration that functionality and data integrity was intact

- All problems are logged

- No excessive re-requests of data during the tests

- Limited system errors generated by users in system logs

# 4. 	Participant Responsibilities and Data Guidelines

## 4.1.	Participant Responsibilities

The following list details the responsibilities of all JSE Yield-X Market Dress Rehearsal participants:

- Participants are responsible for all of their own environment preparations, connectivity and reference data download

- All users to log on and participate in the test

- Ensure that all fields are displayed correctly and as expected

- Ensure that all fields are enterable as expected

- Check that invalid field entries are not allowed

- Check that you have access to all functionality that you expect and not more or less

- Does all this functionality operate as expected

- Regular checkpoints will be communicated throughout the test by the JSE.  Any participant falling behind the schedule must communicate this to the JSE as soon as possible.  Likewise if the schedule is required to change, this will also be communicated to the market.

- All Software bugs may be logged following the error logging procedure. Any other issue encountered during Dress Rehearsal must be logged with JSE Client Services (011-520 7777)

## 4.2.	Data Guidelines

The following are key data guidelines:

- Valid user codes and passwords must be used for all application access

- Realistic prices and volumes must be entered

- Data will be converted from production for the Dress Rehearsals and should therefore be correct data

## 4.2.	Communication

The JSE will communicate with all testers in a number of different ways:

- A message via the front end

- An email to all know email addresses

- An SMS to known cell phone numbers (please confirm that JSE Client Services has the correct number for SMS status updates during the Dress Rehearsal)

- The JSE will communicate progress, issues and status of the tests using the above communication mechanisms.

Any JSE Yield-X Market Dress Rehearsal queries can be directed to JSE Client Services on 011 520 7777 or yield-x_info@jse.co.za

| DRESS REHEARSAL SCHEDULE |  |  |  |
| --- | --- | --- | --- |
| Ref # | Trading Phase | Trading Times | Functionality to be tested |
|  |  | (SAST) | (High-level Description) |
| FRIDAY |  |  |  |
| Checkpoint 1 - Balancing of Environments |  |  |  |
| A | Balancing of Environments | 17h30 | Clearing Members to Balance Production and new Yield-X Environments. |
| B | JSE Margin Reconversion | 19h00 | JSE re-converts |
| Checkpoint 2 – Backup of Environment |  |  |  |
| C | Backup of Environment. | 20h30 | JSE and Clearing Members to make a Backup of the new Yield-X environment, for Rollback purposes. |
| SATURDAY |  |  |  |
| A | Market Startup | 08h00 | File Preparation Check Market times |
| Checkpoint 1 – User Login |  |  |  |
| B | All users to log in. | 08h30 - 09h00 | All API front end and Information subscribers to Log In. Users with access to CDD and EDM front ends to log these into the JSE production environment as well |
| Checkpoint 2 – Continuous Trading |  |  |  |
| C | Continuous Trading: - Currency Derivatives - Bond Derivatives - Spot Bonds | 09h00- 11h00 | Users to enter orders |
| C1 | Margin Reconversion | 09h00 – 11h00 | Clearing Members only |
| Checkpoint 3 - Market Checkpoint |  |  |  |
| D | VOLUME TESTING Continuous Trading | 11h00 - 11h30 | Volume Testing: Simulated Volumes |
| Checkpoint 4 - Trading Phase Change-over |  |  |  |
| E | Admin Period | 11h30 – 11h45 | No On Screen Trading Report only trades allowed Allocations allowed Deal Management allowed |
| Checkpoint 5 - Trading Phase Change-over |  |  |  |
| F | Market Closed | 11h45 | Market Closed Users may download EOD data (deals, positions) via API or JSE Front End Publishing of closing prices |
| G and H | Exchange proceeds with End of day Clearing Members to download Balancing to Clearing Members | 11h45 – 13h00 | 31 October 2009 DR only |

| POST DRESS REHEARSAL SYSTEMS CLEANUP – TECHNICAL TEAMS ONLY |  |  |  |
| --- | --- | --- | --- |
| SATURDAY |  |  |  |
| I | JSE and Clearing members to Roll back their new Yield-X environments to state as at Friday post EOD | 13h00 - 14h00 | Rollback to state prior to Dress Rehearsal. |
| Checkpoint 6– Rollback Testing |  |  |  |

# Market Dress Rehearsal Functional Testing Checklist

| Friday: Clearing Member participation mandatory |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CM – Clearing Members |  |  |  |  |  |  |  |  |
| CDD – CDD Members |  |  |  |  |  |  |  |  |
| EDM – EDM Members |  |  |  |  |  |  |  |  |
| IS – Information Subscribers |  |  |  |  |  |  |  |  |
| Trading Phase |  | Ref # | Action / Event | Expected Result | Applicable To | Completed (Y/N) | Successful (Y/N) | Comments |
| Check Point 1 |  |  |  |  |  |  |  |  |
| Friday: Clearing Member Balancing | 17h30 – 19h00 | A1 | Clearing Members to balance both Yield-X Production and Yield-X new environment | Clearing Members balance and have correct MTM, Deals and Positions files for Friday | CM |  |  |  |
| JSE Margin Reconversion | 19h00 | B1 | JSE performs Margin Reconversion | Preparation to allow balancing to clearing members on Dress Rehearsal | JSE |  |  |  |
| Check point 2 |  |  |  |  |  |  |  |  |
| Friday: Backup of Environments | After Balancing | C1 | JSE backs up Yield-X new environment, for Rollback purposes after Dress Rehearsals | JSE Yield-X | JSE |  |  |  |
|  |  |  |  | New Production environment |  |  |  |  |
|  |  |  |  | backed up |  |  |  |  |
|  |  | C2 | Clearing Members backup their Yield-X systems, for Rollback purposes after Dress Rehearsals | Clearing Members’ | CM |  |  |  |
|  |  |  |  | New Yield-X environments |  |  |  |  |
|  |  |  |  | backed up |  |  |  |  |

| Saturday: Full participation mandatory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Note: The shaded steps are performed by the JSE and have been included for a level of functional understanding. Reference numbers highlighted in yellow indicate technical actions and in blue indicate business steps. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CM – Clearing Members Yield-X – Yield-X Members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CDD – CDD Members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDM – EDM Members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IS – Information Subscribers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase |  | Ref # | Action / Event | Expected Result | Applicable To | Completed (Y/N) |  |  | Successful (Y/N) | Comments |  |  |  |  |  |  |  |  |
| Saturday: Market Startup | 08h00 | A1 | File preparation | Market started | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Check market times |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saturday: User Login | 08h30 – 09h00 | B1 | All API users, JSE Font End users and Information Users login and subscribe to instruments | Users logged into market | CM Yield-X CDD EDM IS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saturday: Clearing Member Reconversion | 09h00 – 11h00 | C1 | Clearing Member Margin Re-conversions | Clearing Members re-conversion | CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saturday: Continuous Trading | 0900 – 11h00 | C2 | Insert Orders (Spot Bonds, Bond Futures, Currency Futures, Options on instruments that permit options to be traded) | Orders inserted Orders suspended/deleted | Yield-X CM CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C3 | Resubmit Orders | Orders resubmitted | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saturday: Continuous Trading | 09h00 – 11h00 | C4 | Reduce Orders | Orders reduced | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C5 | Edit Orders | Orders edited | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C6 | Cancel Orders | Orders cancelled | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C7 | Information Subscribers listen to Screen / Price Updates. | Screen / Price Updates received. | IS Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C8 | Enter Report Only Trades | Report Only orders entered | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C9 | Accept Report Only trades | Report Only orders accepted | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C10 | Option Exercise | Options exercised | Yield-X CDD EDM CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C11 | Option Abandon | Option abandoned | Yield-X CDD EDM CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C12 | Enter Tri-partite Deal | Tri-partite Deal entered | Yield-X CDD EDM CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C13 | Roll position forward | Position closed out and booked into another position | Yield-X CDD EDM CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C14 | Load Clients | Clients loaded | Yield-X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C15 | Edit Clients | Clients details updated | Yield-X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C16 | Assign trades | Trades assigned | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C17 | Div Trades | Trades are Divided | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C18 | Cumulate Trades | Trades cumulated | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 5 |  |  |  |  |  |  |  |  |  |  |  | F1 | Simulate average futures closeout volumes Entry of Report only trades (No On Screen Trading Allowed) | High Volumes Simulated Report Only trades entered | CM CDD EDM IS CM CDD EDM |  |  |  |
| Saturday: Volume Test | 11h00 – 11h30 | D | Users to increase order volumes on Yield-X, CDD and EDM | Report Only trades edited | Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 6 |  |  |  |  |  |  |  |  |  |  |  | G1 | Accepting/rejecting report only trades | Report Only trades accepted/rejected | CM CDD EDM |  |  |  |
| Saturday: Admin Period | 11h30 – 11h45 | E1 | Assign (allocate) trades | Trades assigned | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | E2 | Split Trades | Trades split | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | E3 | Cumulate Trades | Trades cumulated | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | E4 | Silo Receipts & Physical Deliveries | Silo Certificates and Delivery Notices entered | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | E5 | Market Closes | Market Closed | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 7 |  |  |  |  |  |  |  |  |  |  |  | H1 | Market Closes Exchange performs EOD run (MTM & Margining) | Market Closed EOD run successfully | JSE |  |  |  |
| Saturday: Market Closed | 11h45 | F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 8 |  |  |  |  |  |  |  |  |  |  |  | I1 | Make MTM File available for download | MTM File available for download (by all participants) | JSE |  |  |  |
| Saturday: Run EOD | 11h45 – 12h00 | G | Make Daily Account Summary available for download | Daily Account Summary available for download | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 9 |  |  |  |  |  |  |  |  |  |  |  | J1 | Clearing Members advised by Exchange that MTM file and Daily Account Summary can be downloaded | Clearing members notified | JSE |  |  |  |
| Saturday: 31 OCTOBE R 2009 ONLY Clearing Member Balancing | 12h00 – 13h00 | H1 | Clearing Members download MTM file & Daily Account Summary | MTM and Daily Account Summary downloaded | CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H2 | Clearing Members run their EOD processes | Clearing Members processes run | CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H3 | Clearing Members balance to Exchange | Clearing Members balanced to Exchange | CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H4 | Clearing Members run their EOD processes | Clearing Members processes run | CM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H5 | Billing files for ACCPAC generated | Billing files for ACCPAC generated | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H6 | SWIFT payment instruction messages generated | SWIFT payment instruction messages generated | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check Point 10 |  |  |  |  |  |  |  |  |  |  |  | K1 | Files for BDA & CAPAD generated | Files for BDA & CAPAD generated | JSE |  |  |  |
| Saturday: EOD Downloads | 12h00 – 13h00 | H7 | Create EOD Reports | EOD Reports created | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H7 | Create EOD Files | EOD Files created | JSE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H8 | API Users, Front End users and Information users download MTM file | MTM file downloaded | Yield-X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H9 | Subscribers download EOD files | EOD files downloaded | Yield-X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H10 | EOD Reports to SAFEX web site (free to air) | EOD reports can be viewed on web | Yield-X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saturday: Rollback to Yield-X Production Systems - Full TECHNICAL participation mandatory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note: This is to restore Yield-X systems to their state as at end of Friday, so that production parallel can continue on Monday. |  |  |  |  |  |  |  |  |  |  |  |  | JSE to Roll back their Release C Environment to state as at Friday the 8th of June | Successful Rollback of systems | JSE |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Clearing Members to Roll Back their Release C systems to state as at Friday the 8th of June | Successful Rollback of systems | CM |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | L1 |  |  |  |  |  |  |
| Saturday Roll Back | 13h00 – 14h00 | I1 | Rollback of JSE Systems and Clearing Member Yield-X, CDD and EDM to state as at end of day on Friday before Dress Rehearsal |  | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Ensure no data remains resident for live trading on Monday post the Dress Rehearsal |  | CM Yield-X CDD EDM |  |  |  |  |  |  |  |  |  |  |  |  |  |

# 7. 	Market Dress Rehearsal Detailed Checklist

To be returned to the JSE as per instructions in Section 3.2.

Member Firm Name:_______________________________	Date:_____________________

Market Dress Rehearsal Detailed Check-list completed by:

Name:				_______________________________

Position:			_______________________________

Company code /Member ID:	_______________________________

Signature			_______________________________

I hereby declare that all information contained here-in is an accurate reflection of the test conditions executed on behalf of my organisation.

Signed by Head of Trading:

Name:		_______________________________

Signature	_______________________________

Signed by IT representative:

Name:		_______________________________

Signature	_______________________________

General Comments: _____________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________